## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Lose team members | One or more team members drop the class | 1 | 5 | 5 | 25 | Team leader and all members | 2022-05-16 | Redefine the project scope if necessary, and assign the tasks to other team members. | Ingor dropped course and Jing will take over this tasks | Closed
| add new team members | One or more students are added to the team | 1 | 1 | 1 | 25 | Team leader | 06/01/2022 | Re-arrange works to make sure every team member has equally shared workload | For each group, members have been fixed and it's unlikely that more personnel changes will happen | Closed
| Lack of motivation or responsibility | One or more team members are not motivated and not willing to contribute | 3 | 5 | 4 | 12 | All members | End of semester | Hold an additional meeting to identify the reason and report to the professor if necessary | Everybody is enthusiastic to work and wiling to contribute | Open
Communication | duplicate work | Two or more team members mistakenly did the same or similar work | 2 | 2 | 2 | 32 | All members | End of semester | Be as detailed as possible when assigning work | In-team communication is efficient so far | Open
| worked on wrong components | One or more team members mistakenly worked on wrong part of the project | 1 | 5 | 3 | 15 | All members | End of semester | Be as detailed as possible when assigning work | In-team communication is efficient so far | Open
| useless work | One or more team members worked on something that is not helpful to the project | 1 | 3 | 3 | 45 | All members | End of semester | Discuss the needs clearly in the meeting and clarify what each team member needs to do | Specific work content has not been assigned yet | Open
| inconsistent work | The features and requirements of the project are not consistent | 1 | 3 | 3 | 45 | All members | End of semester | Ensure that requirements are explained in detail and regularly checked to ensure that all work is in compliance | Detailed requirements are still under discussion | Open
Requirements | unclear requirements | Some part of project requirement was not clarified | 1 | 1 | 1 | 25 | All members | 05/17/2022 | Make sure every part of the work is explained in detail | Specific work content has not been assigned yet | Closed
| scope creep | There are changes and uncontrolled growth in a project’s scope after start | 1 | 5 | 3 | 15 | All members | End of semester | Set scope in detail at the beginning of the project, and be careful with each change. | Scope are defined clearly so far | Open
| constant requirements changes | Some parts of project are constantly need to be changed | 3 | 3 | 4 | 36 | All members | End of semester | Make sure to fully discuss before each change (to avoid meaningless changes) | Our project has just started, and this problem has not occurred yet | Open
Management | improper task assignments | Assigning a task to a member that is incapable of doing the task | 2 | 4 | 3 | 24 | All members | End of semester | If anyone gets lost, make sure to voice your concern immediately. | All team members are willing to communictate so far | Open
| improper planning | The team leader's plan is not appropriate | 1 | 5 | 5 | 25 | Team leader | 05/17/2022 | Carefully discuss the whole plan and fix any problem as soon as they arise | Our project plan works fine | Closed
| lack of management skills | One or more leader has Insufficient management skills | 1 | 3 | 3 | 45 | Team leader | 05/17/2022 | Identify the weakness and start to learn lacking management skills as soon as possible | Our team leader has good management skills | Closed
Technology competence | Not familiar with the framework used | One or more team members are not familiar with the framework needed to work on | 4 | 5 | 4 | 8 | All members | 05/31/2022 | Use online tutorials to quickly learn necessary knowledge, and ask team members or professor if any question occurs | Every member is willing to learn so far | Open
| Not familiar with the programming language used | One or more team members are not familiar with the programming language used for the project | 1 | 2 | 3 | 60 | All members | 05/31/2022 | Use online tutorials to quickly learn necessary knowledge, and ask team members or professor if any question occurs | Every member is willing to learn so far | Closed
| Not familiar with unit testing | One or more team members are not familiar with the unit testing procedure | 2 | 3 | 3 | 36 | All members | 05/31/2022 | Use online tutorials to quickly learn necessary knowledge, and ask team members or professor if any question occurs | Every member is willing to learn so far | Closed
| Other technology incompetence | One or more team members are not familiar with other technology that is related to the project | 2 | 3 | 3 | 36 | All members | 05/31/2022 | List in detail what needs to be used and learned, and utilize network resources to solve problems | None technoloy incompetence occured yet | Closed
| Not familiar with Git | One or more team members are not familiar with git or Github usage | 1 | 2 | 2 | 40 | All members | 05/17/2022 | Read the git tutorial | Everyone's familier with git | Closed
Design and implementation | Improper design | One or more part of the project is not designed correctly and have some problems | 1 | 5 | 5 | 25 | All members | 05/31/2022 | Discuss project design in meeting and consider everything carefully. | No problem has been found in the project design is well so far | Closed
| improper technology stack | The programming languages, frameworks, and tools that decided to use are proved to be improper | 1 | 1 | 3 | 75 | All members | 05/31/2022 | Discuss technology stack in meeting and make sure that the technologies we're using are suitable for development | No problem has been found in the technology stack so far | Closed
| Messy code | Code is not well structured/commented and thus very hard to understand | 3 | 2 | 2 | 24 | All members | 06/14/2022 | Review code before merging. Rewrite the code, if the code does not meet the standard | Haven't started writing code yet | Open
Testing | Not enough testing | Team didn't fully test the app in every scenario | 2 | 2 | 2 | 32 | All members | 06/14/2022 | Make sure to plan everything ahead of time. Finish basic and necessary tests first. | Haven't started testing yet | Open
Integration and deployment | Not enough time for integration and deployment | Team failed to integrate and deploy the app in time | 3 | 5 | 5 | 15 | All members | 06/14/2022 | Make sure to plan everything ahead of time. If time is really not enough, ask the professor if it is possible to extend the delivery time | Haven't started integration or deployment yet | Open