## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/10-05/16 | Set up meeting times and communication tools. Got to know each team member and discussed all perspectives of the project. Decided the project topic, MVP, and optional features. Did work allocation of iteration 0 of the project and all members have completed their work. Reviewed the existed code and set up learning targets. Future task responsibilities were also discussed and assigned among team members. | Initial meeting tool was free Zoom meeting, had to create multiple sections. |  | Plan and accomplished iteration 1 requirements. Learn unit test, integration test, Django Learn and demo initial code | 0 | 0 | 0 | 0 | 0 | 54.75 | 38.75 | 3.2 | 13 | 5 | 1 | 0 | 2 | 9.75 | 4.5 | Test case pass Customer Rating
1 | 05/17-05/30 | Had 4 weekly meetings for sprint planning and progress updates. Reviewed progress and set up learning targets. Finished user stories of all the essential and optional features. Did work allocation of iteration 1 and all members have completed their work. Wrote and reviewed unit test and integration test code. Discussed future tasks and assigned among team members. | API |  | Continue to update project progress and allocate tasks Finish learning objects and answer any questions or concerns. Finish another one or two features in the next Sprint. Continue automated testing and update code. | 2 | 6 | 0 | 0 | 0 | 107.1 | 89.5 | 4.4 | 23.5 | 6 | 7.5 | 17 | 11 | 12 | 3 | Cost # of Feature completed Test case pass Customer Rating
2 | 05/31-06/13
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## SylvieXiang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/10-05/16 | 12.7 | 9.5 | 3.2 | 0 - learn git and read several tutorials 5 - make project plan, finishing multiple documents 6 - set up git 7 - presentation | 3 |  |  |  |  | 3 | 1.5 | 2 | Write management plan section of SPPP write meeting minute document Persentation iteration 0 | Started late of the week, need more time | Going to start first weekly meeting early next week | 0 - learn Django and unit testing 1 - check out and familiarize with code 2 - design features 5 - continue to have weekly meeting 6 - push or merge code | 8
2 | 05/17-05/23 | 10 | 7.5 | 2.5 | 0 - learn Django, Sprint, PivotalTracker, and several tutorials 1 - write stories 2 - design features 5 - make sprint plans, write documents | 3 | 1.5 | 1.5 |  |  | 1.5 |  |  | write sprint planning, write meeting minute | not familar with PivotalTracker, needed to spend some time to finish task | read tutorial and learned from demo and did more research | 0 - learn unit test, selenium 1 - continue to check out and familarize with code 2 - continue on design 5 - continue to have sprint planning with team | 8
3 | 05/24-05/30 | 17.4 | 15.5 | 1.9 | 0 - learn integration test 3 - write integration test framework, code, and direction 4 - integration testing with selenium 5 - make sprint plan, write multiple documents | 3.5 |  |  | 6 | 4 | 2 |  |  | write sprint planning, write meeting minute, write different sections of documentation | did not know integration test, needed to spend a good amount of time to familiarize with it | research selenium, read and studied integration test | 0 - familiarize with unit test 3- continue on integration test code writing 4 - continue to do integration test 5 - continue to have sprint planning with team | 10
4 | 05/31-06/06
5 | 06/07-06/13
6 | 06/14-06/20

## Serguei Chervachidze
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10.2 | 7 | 3.2 | 0 - learn git and read several tutorials 5 - make project plan, finishing multiple documents 6 - set up git 7 - presentation | 1 | 1 | 1 |  |  | 2 | 1 | 1 | - write overview, proposal high level, and related work sections of SPPP - upload initial code for the front end of the porject - initial planning for design of the application and implementation details - initial analysis of requirements Persentation iteration 0 | Started latr in the week, need more to move faster | We will continue to meet and communicate more frequently and push on the project | 0 - Upload initial existing code for front end 1 - Do a PR with the barebones (standard) Django app 2 - Start fleshing out design patterns/implementation details 3 - Help team members with questions on Django or existing frontend code | 9
2 | 05/17-05/23 | 13.5 | 11 | 2.5 | 0 - learn PivotalTracker, 1 - write stories 2 - design overall architecture 3 - write initial app code 5 - make sprint plans, write documents | 2 | 1.5 | 3 | 3 |  | 1.5 |  |  | write specification docs, commit code, train other team members of Django | not familar with PivotalTracker, | read tutorials | 0 - learn unit test 1 - continue to make sure we have all neccessary libs 2 - continue on design 3 - continue with implementation 5 - continue to have sprint planning with team | 8
3 | 05/24-05/30 | 13.9 | 12 | 1.9 | 0 - learn Django unit testing 2 - refine architecture design 3 - Write code for the backend interacting with frontend (no forecasting for now) 5 - make sprint plan, write multiple documents | 2 | 1 | 3 | 3 | 1 | 2 |  |  | developed first working code of both backend and frontend | public api for stock symbols went offline temporrily, inhibiting development | continue implementing features and working on docs | 2 - continue on design 3 - continue with implementation 5 - continue to have sprint planning with team | 10

## Duy Nguyen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 8.95 | 5.75 | 3.2 | 0. learn Git, Django, unit tests 5. Quality Assurance Plan portion for SPPP 5. communication/ feedback gathering with team. 5. Progress report 7. Code Review Checklist | 2 |  |  |  |  | 3.25 |  | 0.5 | Write Quality Assurance portion of SPPP Team meeting. Screen shared during meeting to navigate and captured secondary notes | 1. not familiar with Django, Git 2. not familiar with Quality Assurance for Software | 1.Learn more about Django and Git. Start testing branching and merging. 2. Start on Unit test development with existing codes 3. Meet earlier in week so I have more time to learn before tackling assignments | 4. Unit Test for existing codes 1. Continue to fine tune Quality Assurance Plan with Code Review Checklist 0. Finish Django tutorial. 7. Start preping presentation if possible | 15
2 | 05/17-05/23 | 10.5 | 8 | 2.5 | 0. Unit Test Tutorials, Django Tutorials 3. codes for unit test for ulr 4. Unit tests for URL's 5. Pivotal Tracker Stories/ class diagram | 3 |  |  | 2 | 1 | 2 |  |  | reviewed and push PR's. | 1. not familar with software testing | 1. learning a lot through online tutorials 2. |  | 12
3 | 05/24-05/30 | 14.9 | 13 | 1.9 | 0. Unit Test Tutorials 3. codes for unit test for views 4. Perform Unit tests for Views/manual end-to-end testing 7. Presentation ,Code Demo, STD document, Test Report | 3 |  |  | 3 | 3 |  |  | 4 | -Wrote unit tests to test URL and views. -Put together presentation and Code Demo -Test reports | 1. not familiar with software testing 2. couldn't get app to run for a while(figured it out after some time) | 1. learning a lot through online tutorials 2. Fixed. It was a problem with my http server for python | 4. Change tests to select a random stock to test instead of hardcoding. 5. change code to check a random stock that isn't on list to see if it'll throw error | 15

## Jing Tian
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 11.7 | 8.5 | 3.2 | 0. learn Git, Django, unit tests 1. Risk Management document 2. 3. 4. 5. Set up zoom meetings and inform team members 6. Set up git. Set up python and Django environment 7. | 3 | 4 | 0 | 0 | 0 | 0.5 | 1 | 0 | 1.Analyze and write risk management document. Book and hold zoom meeting for the team. 2.Create git repo and set up some templates for team to use. | 1. Not familiar with Django. 2. I don't know anything about security executives. I need to learn how to be a security leader and what I should do. | 1.Learn more about Django. 2.Learn more about git&github. 3.Learn how to be a good security leader and figure out what is necessary to be done. | 1. Learn more about Django and get familer with existing code. 2. Learn more about security leader's role. 3. Do some code-writing practice along with learning objectives. | 15
2 | 05/17-05/23 | 12 | 9.5 | 2.5 | 0 - learn PivotalTracker and Django 1 - Write individual stories (lab2) 5 - make sprint plans, write documents 6 - Install requirements, set up local server, backend and frontend | 4 | 2 | 0 | 0 | 0 | 1 | 2 | 0.5 | Updated risk management document Updated assigned part in SPPP Added test cases in STD | First using PivotalTracker, and not familier with Django | 1. Learn more about Django 2. Learn more about PivotalTracker | 0 - Learn Django and unit test 3 - Finish enviroment setup and start to implement features 5 - Continue to have sprint planning with team | 10
3 | 05/24-05/30 | 14.9 | 13 | 1.9 | 0 - learn Django and unit testing 4 - Manual testing 5 - Write and update multiple documents 6 - Set up anaconda virtual envirnoment, run code 7 - Presentation | 3 | 0 | 0 | 0 | 2 | 2 | 1 | 5 | Updated risk management document Updated assigned part in SPPP Added test cases in STD | Failed to connect to api sometimes. Django structure is more complicatedthan I expected. | 1. Learn more about Django 2. Find some replacement api for our project | 0 - Keep learning Django and unit test 3 - Start to implement features, write code. 5 - Continue to have sprint planning with team | 10

## Igor Kheyfets
Your Lead Roles: Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 11.2 | 8 | 3.2 | 0 - review git branching, learn Django, watch tutorials on react, research financial apis 4 - test inital code 5 - Requirements management plan for SPPP 6 - Configure git/venv | 4 |  |  |  | 2 | 1 | 1 |  | 1. Write 1 section of SPPP 2. Establish virtual environment 3. Review initial code | 1. react still feeels foreign | 1. Taking a Codecademy course on React | 1. Continue to learn React 2. Help team with Django 3. Research Facebook Prophet and read documentation | 6