## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet was completed by the team leader(Sylvie) at the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/10-05/16 | Set up meeting times and communication tools. Got to know each team member and discussed all perspectives of the project. Decided the project topic, MVP, and optional features. Did work allocation of iteration 0 of the project and all members have completed their work. Reviewed the existed code and set up learning targets. Future task responsibilities were also discussed and assigned among team members. | Initial meeting tool was free Zoom meeting, had to create multiple sections. | NA | Plan and accomplished iteration 1 requirements. Learn unit test, integration test, Django Learn and demo initial code | 0 | 0 | 0 | 0 | 0 | 41.95 | 38.75 | 3.2 | 13 | 5 | 1 | 0 | 2 | 9.75 | 4.5 | Test case pass Customer Rating
1 | 05/17-05/30 | Had 4 weekly meetings for sprint planning and progress updates. Reviewed progress and set up learning targets. Finished user stories of all the essential and optional features. Did work allocation of iteration 1 and all members have completed their work. Wrote and reviewed unit test and integration test code. Discussed future tasks and assigned among team members. | Alphavantage API was down | NA | Continue to update project progress and allocate tasks Finish learning objects and answer any questions or concerns. Finish another one or two features in the next Sprint. Continue automated testing and update code. | 2 | 6 | 0 | 0 | 0 | 93.9 | 89.5 | 4.4 | 23.5 | 6 | 7.5 | 17 | 11 | 12 | 3 | Cost # of Feature completed Test case pass Customer Rating
2 | 05/31-06/13 | Had 4 weekly meetings for sprint planning and progress updates. Reviewed progress and set up work allocation Finished essential features and added one optional feature Used API URLs from config file Completed all individual work for iteration 2 Discussed future tasks and assigned among team members Set up survey for customer rating and market feedback | Unable to load API keys URLs from configuration file, wrote code to parse config file | SDD file misunderstanding from the facilitator. Communicated and were confirmed that there is no problem | Finish project requirements and allocate tasks Finish all required documentations Finsih testings and update code Gather results from customer ratings/market feedback | 8 | 0 | 0 | 0 | 0 | 79.6 | 76 | 3.6 | 12 | 0 | 5 | 17.5 | 24 | 11.5 | 1 | Cost # of Feature completed Test case pass Customer Rating
3 | 06/14-06/20 | Had 2 weekly meetings for sprint planning and progree updates. Finalized project and set up work allocation. Finished all testings. Added config file vaildation test and directions Gathered survey results. Completed all individual work for iteration 3. | NA | NA | NA | 11 | 0 | 0 | 0 | 0 | 38.4 | 36 | 2.4 | 0 | 0 | 0 | 1 | 7 | 22 | 0 | Cost # of Feature completed Test case pass Customer Rating

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Sylvie Xiang | 2022-01-04 | wrote 3 feature user stories wrote multiple chores | NA | 2022-01-03 | iteration 0 & 3 | Designed and implementated the "Save as Favorite" feature | - set up integration test - refactored unit test, - modified integration test, - fixed chart display bug after "forecast" feature implementated | NA | - Reviewed and provided improvement suggestions for majorities of the PRs to ensure code quality. - Made PowerPoints for iteration 0 and 3, presented as well. - Wrote agendas for every meeting - Made Sprint planning for all iterations - In charged of Progress Report and Meeting Minutes. - Reviewed and revised all documentations before every submissions. - Submitted and released iterations 0, 1, and 3. - Meeting taker for 8 meetings - Communicated with professor, facilitator and other team leaders regarding project questions. - Kept track of project progress and followed up with members progress | Every member was hard working and responsible
Duy Nguyen | 6,7 | wrote 2 feature user stories | NA | 1,2,4 | iteration 1 & 3 | N/A | backend Unit test, Manual test , Front End - Card.js unit test. I wrote unit test for all methods within the Views and Urls portion of the backend. I also wrote unit test for methods in Card.JS. Performed Manual tests on the app itself and filled out the test reports. | NA | Made Test Report, and Survey Monkey's MFA. Took notes for Meeting 2 and 9. Made powerpoint presentation for iteration 1 as well as presented for iteration 1. | I am extremely lucky to be apart of team3. Everyone was very hardworking and responsible. Team Leader, Sylvie was able to make and assign tasks promptly while implementation leader, Serguei was extremely helpful with codes. Although we lost a team member in Igor, Jing was able to step up and performed extremely well.
Jing Tian | 4.b, 5 | wrote 2 feature user stories | NA | 2 | iteration 1 & 3 | NA | Maual test, Unit test for configuration file | I set up configuration file for API URLs used in our project. This would only allow use to use thier locally stored API URLs. Thus prevent different users sharing same APIs and causing overuse problem. I also added configuration file to gitignore so personal APIs will not be uploaded to the repo | Made Risk Managment for the project and keep updating in each iteration Schedule and manage all weekly meetings. Contribute making powerpoint for iteration 1 presentation. Made Demo for iteration 1. Took notes for meeting 6 and meeting 8. | I love everyone on my team. As a rookie, I firstly struggled a lot to understand the new framework, but my team members are very enthusiastic to teach me new things. Our team leader Sylvie is very attentive in management and arrangements. Serguei, our design and implementation leader, is very knowledgeable and helpful, not only coding but also explaining structures and framework to us. Duy, our quality assurance leader, is very nice and friendly. During the testing, he tested various aspects of our code very carefully. I was very lucky my teammates carried me, many thanks to everyone in my team!
Serguei Chervachidze | 2022-01-03 | - configured Pivotal tracker for team needs (sprint length, story types, etc) - wrote 3 feature user stories - wrote a large number of chores | ALL (entirety of the SDD) | 1 | iteration 2 & 3 | - contributed orginal code for the front end of the project - set up initial Django app - set up the initial frontend implementation - implemented the back end in Django (views, data processing, etc) around fetching data from public API's - extended the backend to allow for forecasting by implementing the "Stock Price Forcast" feature using facebook prophet ML algo: Forecaster and ProphetModel classes - extended the front end to support forecasting ("Stock Price Forecast" feature) by extending the front end UI (drop-down boxes, spinner, etc) - extended the backend to support multiple types of forecasting models (for now just uses prophet only) | - implemented unit tests around forecasting machinary in the back end (for Forecaster and ProphetModel classes) | - Set up and configured the original Django app - Set up and configure the app foler structure for both backend and frontend - Set up requirements.txt needed for the project implementation | Came up with the idea for the project. Helped drive team discussions and ideas. Helped team learn/adopt Agile practices. Made PowerPoints for iteration 2 and 3. | Being part of Team 3 has been a terrific experience. Everyone worked hard, and we were able to deliver our product. Had a lot of fun.

## SylvieXiang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 12.7 | 9.5 | 3.2 | 0 - learn git and read several tutorials 5 - make project plan, finishing multiple documents 6 - set up git 7 - presentation | 3 | 0 | 0 | 0 | 0 | 3 | 1.5 | 2 | Write management plan section of SPPP write meeting minute document Persentation iteration 0 | Started late of the week, need more time | Going to start first weekly meeting early next week | 0 - learn Django and unit testing 1 - check out and familiarize with code 2 - design features 5 - continue to have weekly meeting 6 - push or merge code | 8
2 | 05/17-05/23 | 10 | 7.5 | 2.5 | 0 - learn Django, Sprint, PivotalTracker, and several tutorials 1 - write stories 2 - design features 5 - make sprint plans, write documents | 3 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | write sprint planning, write meeting minute | not familar with PivotalTracker, needed to spend some time to finish task | read tutorial and learned from demo and did more research | 0 - learn unit test, selenium 1 - continue to check out and familarize with code 2 - continue on design 5 - continue to have sprint planning with team | 8
3 | 05/24-05/30 | 17.4 | 15.5 | 1.9 | 0 - learn integration test 3 - write integration test framework, code, and direction 4 - integration testing with selenium 5 - make sprint plan, write multiple documents | 3.5 | 0 | 0 | 6 | 4 | 2 | 0 | 0 | write sprint planning, write meeting minute, write different sections of documentation | did not know integration test, needed to spend a good amount of time to familiarize with it | research selenium, read and studied integration test | 0 - familiarize with unit test 3- continue on integration test code writing 4 - continue to do integration test 5 - continue to have sprint planning with team | 10
4 | 05/31-06/06 | 6 | 4 | 2 | 2 - design user registeration 3 - write code for registeration 4 - test written code 5 - make sprint plan and meeting agenda | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | write sprint planning, meeting agenda, unit test code refactored | forgot parameterized | research and read about parameterized library | 1- Manage SPPP 3 - write code for an optional feature 4 - integration test for new code with exsisted code 5 - sprint planning | 9
5 | 06/07-06/13 | 15.1 | 13.5 | 1.6 | 2 - design "save as Favorite" feature 3 - wrote code and fix bug for the feature 4 - integration tests on "forecast"&"Favorite" features 5 - make sprint plan and worte meeting agendas 7 - PRs review | 0 | 0 | 1 | 5 | 5 | 0.5 | 0 | 2 | write sprint planning, meeting agendas, STD and SPPP sections, write feature code and integration tests, PRs review | Code disagreement | Resolved with updating the majors | 1 - manage SPPP 4 - integration tests 5 - sprint planning, review all documentations, presentation | 9
6 | 06/14-06/20 | 12.4 | 10 | 2.4 | 4 - modified test to include longer timeout and delay 5 - made presentation Power Point, sprint plan, and wrote meeting agedas and documentations 7 - Added developer description, PR review | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 1 | Wrote sprint planning, meeting agendas Made presentation power point and presented Modified integration tests PR review Finished mulitple sections of multiple documentations | NA | NA | NA | NA

## Serguei Chervachidze
`
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10.2 | 7 | 3.2 | 0 - learn git and read several tutorials 1 - research django requirements 2 - start working on backend design 5 - make project plan, finishing multiple documents 6 - set up git 7 - presentation | 1 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | - write overview, proposal high level, and related work sections of SPPP - upload initial code for the front end of the porject - initial planning for design of the application and implementation details - initial analysis of requirements Persentation iteration 0 | Started latr in the week, need more to move faster | We will continue to meet and communicate more frequently and push on the project | 0 - Upload initial existing code for front end 1 - Do a PR with the barebones (standard) Django app 2 - Start fleshing out design patterns/implementation details 3 - Help team members with questions on Django or existing frontend code | 9
2 | 05/17-05/23 | 13.5 | 11 | 2.5 | 0 - learn PivotalTracker, 1 - write stories 2 - design overall architecture 3 - write initial app code 5 - make sprint plans, write documents | 2 | 1.5 | 3 | 3 | 0 | 1.5 | 0 | 0 | write specification docs, commit code, train other team members of Django | not familar with PivotalTracker, | read tutorials | 0 - learn unit test 1 - continue to make sure we have all neccessary libs 2 - continue on design 3 - continue with implementation 5 - continue to have sprint planning with team | 8
3 | 05/24-05/30 | 13.9 | 12 | 1.9 | 0 - learn Django unit testing 1 - research Facebook prophet requirements 2 - refine architecture design 3 - Write code for the backend interacting with frontend (no forecasting for now) 4 - manually test front end performance 5 - make sprint plan, write multiple documents | 2 | 1 | 3 | 3 | 1 | 2 | 0 | 0 | developed first working code of both backend and frontend | public api for stock symbols went offline temporrily, inhibiting development | continue implementing features and working on docs | 2 - continue on design 3 - continue with implementation 5 - continue to have sprint planning with team | 10
4 | 05/31-06/06 | 12 | 10 | 2 | 2 - design forecasting (3 hr) 3 - write code for forecasting implementation (4 hr) 4 - test written code around forecasting in the backend (2 hr) 5 - update sdd technical document (1 hr); communicate with the team | 0 | 0 | 3 | 4 | 2 | 1 | 0 | 0 | implement forecasting code, implement tests for backend forecasting | None | N/A | 4 - concentrate on testing 5 - prepare team presentation 5 - update sdd | 10
5 | 06/07-06/13 | 11.6 | 10 | 1.6 | 3 - write code for UI update around forecasting (2 hr) 4 - test written code (5 hr): additional tests for backen forecasting implementation 5 -update sdd technical document and prepare team presentation for iteration 2 (3 hr) | 0 | 0 | 0 | 2 | 5 | 3 | 0 | 0 | - implement UI update around forecasting - implement additional unit tests on forecasting in the backend - update sdd - prepeare iteration 2 presentation for the team | Some bugs found and fixed | N/A | 4 - concentrate on backend unit tests 5 - help prepare final team presentation 7 - prepeare product for final realease | 10
6 | 06/14-06/20 | 8.4 | 6 | 2.4 | 3 - write code for the bugfix on backend/frontend 4 - manual testing end-to-end 5 - made presentation Power Point, and updated SDD document 7 - PR review | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | - Bugfix for backend and frontend - PR review - Testing - Final presentaiton prep | NA | NA | NA | NA

## Duy Nguyen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 8.95 | 5.75 | 3.2 | 0. learn Git, Django, unit tests 5. Quality Assurance Plan portion for SPPP 5. communication/ feedback gathering with team. 5. Progress report 7. Code Review Checklist | 2 | 0 | 0 | 0 | 0 | 3.25 | 0 | 0.5 | Write Quality Assurance portion of SPPP Team meeting. Screen shared during meeting to navigate and captured secondary notes | 1. not familiar with Django, Git 2. not familiar with Quality Assurance for Software | 1.Learn more about Django and Git. Start testing branching and merging. 2. Start on Unit test development with existing codes 3. Meet earlier in week so I have more time to learn before tackling assignments | 4. Unit Test for existing codes 1. Continue to fine tune Quality Assurance Plan with Code Review Checklist 0. Finish Django tutorial. 7. Start preping presentation if possible | 15
2 | 05/17-05/23 | 10.5 | 8 | 2.5 | 0. Unit Test Tutorials, Django Tutorials 3. codes for unit test for ulr 4. Unit tests for URL's 5. Pivotal Tracker Stories/ class diagram | 3 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | reviewed and push PR's. | 1. not familar with software testing | 1. learning a lot through online tutorials 2. |  | 12
3 | 05/24-05/30 | 14.9 | 13 | 1.9 | 0. Unit Test Tutorials 3. codes for unit test for views 4. Perform Unit tests for Views/manual end-to-end testing 7. Presentation ,Code Demo, STD document, Test Report | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 4 | -Wrote unit tests to test URL and views. -Put together presentation and Code Demo -Test reports | 1. not familiar with software testing 2. couldn't get app to run for a while(figured it out after some time) | 1. learning a lot through online tutorials 2. Fixed. It was a problem with my http server for python | 4. Change tests to select a random stock to test instead of hardcoding. 5. change code to check a random stock that isn't on list to see if it'll throw error | 15
4 | 05/31-06/06 | 10.5 | 8.5 | 2 | 0. JS and unit test for JS tutorials 4. attempted test codes for Favorite.JS (couldn't do due to localstorage) 5. updated defect management section to be more robust 5. added issues on Github issues | 3 | 0 | 0 | 0 | 4 | 1.5 | 0 | 0 | 1. Defect Management update I did not have any great deliverables for this week. I tried to have test codes for Favorite.JS but could not figure it out and moved onto card.js | could not figure out how localstorage works on JS. Did not know JS enough to quickly write unit tests | 1. learning more about JS. | 4.write unit test for card.JS 5.finalize survey monkey survey 5. review and update SPPP based on comments | 15
5 | 06/07-06/13 | 12.6 | 11 | 1.6 | 0. JS and unit test for JS tutorials 4. test code for card.JS 5. SPPP update 5. STD update 5. MFA on Survey Monkey survey completed | 3 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 1. card.js unit tests 2. MFA on survey monkey 3. Defect Management 4. Manual Test report | Did not know JS enough to quickly write unit tests. I had to try a bunch of different testing frameworks (mocha, jest and then finally vitest) so there were a lot of trial and errors and inefficiencies | 1. learning more about JS and unit test | 4. complete Card.JS unit tests (there are a lot of methods) 4. start on main.js unit tests | 15
6 | 06/14-06/20 | 13.4 | 11 | 2.4 | 5. Survey Compilation. 5. SPPP update with Survey and metrics results 5. Updated Test Reports 5. Demo presentation 5. Testing portion of group presentation 5. Review all documents for finalization. 7. Survey gathering (friends and family) | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 1 | 1. Survey results 2. SPPP metric results 3. Demo presentation 4. my part of the presentation 5. updated STD | no issues this week, everything went by very smoothly since we had everything planned out with deliverables and action items assigned. | NA | NA | NA

## Jing Tian
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 11.7 | 8.5 | 3.2 | 0. learn Git, Django, unit tests 1. Risk Management document 2. 3. 4. 5. Set up zoom meetings and inform team members 6. Set up git. Set up python and Django environment 7. | 3 | 4 | 0 | 0 | 0 | 0.5 | 1 | 0 | 1.Analyze and write risk management document. Book and hold zoom meeting for the team. 2.Create git repo and set up some templates for team to use. | 1. Not familiar with Django. 2. I don't know anything about security executives. I need to learn how to be a security leader and what I should do. | 1.Learn more about Django. 2.Learn more about git&github. 3.Learn how to be a good security leader and figure out what is necessary to be done. | 1. Learn more about Django and get familer with existing code. 2. Learn more about security leader's role. 3. Do some code-writing practice along with learning objectives. | 15
2 | 05/17-05/23 | 12 | 9.5 | 2.5 | 0 - learn PivotalTracker and Django 1 - Write individual stories (lab2) 5 - make sprint plans, write documents 6 - Install requirements, set up local server, backend and frontend 7 - Organize material needed for presentation | 4 | 2 | 0 | 0 | 0 | 1 | 2 | 0.5 | Updated risk management document Updated assigned part in SPPP Added test cases in STD | First using PivotalTracker, and not familier with Django | 1. Learn more about Django 2. Learn more about PivotalTracker | 0 - Learn Django and unit test 3 - Finish enviroment setup and start to implement features 5 - Continue to have sprint planning with team | 10
3 | 05/24-05/30 | 14.9 | 13 | 1.9 | 0 - learn Django and unit testing 4 - Manual testing 5 - Write and update multiple documents 6 - Set up anaconda virtual envirnoment, run code 7 - Make powerpoint for presenation and record presentation | 3 | 0 | 0 | 0 | 2 | 2 | 1 | 5 | Updated risk management document Updated assigned part in SPPP Added test cases in STD | Failed to connect to api sometimes. Django structure is more complicatedthan I expected. | 1. Learn more about Django 2. Find some replacement api for our project | 0 - Keep learning Django and unit test 3 - Start to implement features, write code. 5 - Continue to have sprint planning with team | 10
4 | 05/31-06/06 | 9.5 | 7.5 | 2 | 0. Learn configuration set-up 3. Modify code to parse local configuration file 4. Manual testing features 5. Update risk management file 6. Set up configuration file | 3 | 0 | 0 | 2 | 1 | 0.5 | 1 | 0 | Updated risk management document Added test cases in STD Add configuration file for API URLs Modified code to parse configuration file | Not fmiliar with cofiguration set-up. | 1. Learning more about Django and unit test 2. Learning more about Python configurations | 4. Write unit test for configuration parsing | 12
5 | 06/07-06/13 | 13.1 | 11.5 | 1.6 | 0. Learn configuration set-up and Django unit testing. Learning how to test configuration parsing 3. Modify code to parse local configuration file 4. Manual testing features 5. STD and risk management document update 7. Add instructions in readme.md for how to set up the app and how to set up local api urls. 7. Submit github release and backboard submission. | 3 | 0 | 0 | 3.5 | 1 | 1 | 0 | 3 | Added test cases in STD Modified code to parse configuration file Added instructions in readme.md for how to set up the app Submit github release | First time submitting github release | 1. Learning more about Python configurations 2. Learning github release procedure | 4. Write unit test for configuration parsing | 12
5 | 06/07-06/14 | 11.4 | 9 | 2.4 | 4. Add unit test for configuration file 5. Add more details in final presentation ppt 7. Ask roomates to fill out our survey. 7. Record presentation | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 3 | Added unit test for configuration file Updated presentation ppt and record part of the final presentation | na | na | 7. prepare final exam :) | na

## Igor Kheyfets
Your Lead Roles: Requirements Leader - No longer in the team
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 11.2 | 8 | 3.2 | 0 - review git branching, learn Django, watch tutorials on react, research financial apis 4 - test inital code 5 - Requirements management plan for SPPP 6 - Configure git/venv | 4 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 1. Write 1 section of SPPP 2. Establish virtual environment 3. Review initial code | 1. react still feeels foreign | 1. Taking a Codecademy course on React | 1. Continue to learn React 2. Help team with Django 3. Research Facebook Prophet and read documentation | 6
No longer in the team